Blackburn BID 2026 Delivery Plan

| Summary |  |
| --- | --- |
| Delivery Plan Manager | Gemma Johnson, Interim BID Manager |
| For Approval By | Blackburn BID Executive Board |
| Period of delivery | January to December 2026 (Term 3 - Year 3) |
| Monitoring & Reporting | The plan will be updated and reported on at each BID Executive Board meeting |
| Stakeholders | Blackburn BID Executive Board Members BID levy payers Blackburn with Darwen BC The Mall Blackburn Lancashire Police Town centre businesses |

Introduction 2026 is year 3 of the third 5-year term of Blackburn BID. The 4 priority themes for this BID term are: - Marketing and promoting the town centre; - Making the town centre safer and more secure, - Making it cleaner, greener and more sustainable; and - Supporting businesses with information & advice. This plan has been developed in line with the Blackburn BID Business Plan Proposal 2024 – 2028 which BID members voted ‘yes’ to. It also has regard to ongoing input and feedback from Blackburn BID Executive Board members, BID members and town centre businesses. The following is the overarching Vision for Year 3 of the Blackburn BID 3: ‘Blackburn BID members feel engaged with the BID, it offers a return on their investment, and the projects and services it delivers improve the town centre offer and benefit their business.’

| PRIORITY THEME 1: MARKETING & PROMOTION |  |  |  |  |
| --- | --- | --- | --- | --- |
| Proposed Spend: £135,500 |  |  |  | Budget |
| Objective | Lead | Supporting partners / Stakeholders | Milestone / Measure of success |  |
| - Promote Blackburn town centre to visitors - Work with partners to deliver a coordinated multi-media programme of marketing and activity which drives footfall to Blackburn town centre. - Deliver Discover Blackburn partnership destination marketing programme. - Utilise digital marketing to highlight Blackburn’s offer including independents and big brands - Integrate the BID website into the Discover Blackburn platform for streamlined management and improved user experience. - Enhance member communications through updated contact databases and the introduction of a WhatsApp channel to ensure timely and relevant information delivery - Provide support and resources to enable businesses to promote themselves. - Facilitate a Marketing working group of board members with option to invite wider stakeholders as appropriate. | Blackburn BID | A Cunning Plan BwD Council The Mall Town Centre event providers | - Increased social media impressions, reach and click-through rates. - Increased traditional media reach. - Increase in social media engagement. - Increased levels of footfall compared with 2025. - Get 50% of BID businesses signed up to the WhatsApp Channel - Increase email open rate for BID member communications |  |
| - Deliver & Support town centre events - Extend commissioned activity to include Eid and Easter. - Commission an external partner to deliver a regular programme of themed, town centre animation and activities for the remainder of the Term. - Create impactful marketing to promote events and activities taking place in Blackburn Town Centre. - In partnership with BwDBC, deliver a Christmas Lights Switch On event on 21/11/26. - Explore the introduction of a Santa’s Grotto in the town centre to enhance the Christmas offer. - Implement targeted social media campaigns featuring human-interest stories from BID businesses to strengthen community engagement. - Work with partners to support the delivery of and promote town centre events. | Blackburn BID | A Cunning Plan BBAC & Events Coordinator External events provider BwD Council The Mall National Festival of Making The Bureau / Blackburn Festival of Light Blackburn Pride Blackburn Cathedral | - Number of animation events delivered - Number of town centre events supported with in-kind and/or financial support. - Increased levels of footfall compared with 2025. - Increased digital & traditional media event marketing reach and engagement. |  |
| - Improve the visitor experience - Work with partners to improve the look and feel of the town centre. - Continue to deliver a Town Centre Ranger Service (see Priority Theme 2) - Create promotional guides to the town centre. | Blackburn BID | BwD Council | - Levels of footfall compared with 2025. - Positive feedback from BID members and visitors |  |

| PRIORITY THEME 2: MAKING THE TOWN CENTRE SAFER & MORE SECURE |  |  |  |  |
| --- | --- | --- | --- | --- |
| Proposed spend: £89,500 |  |  |  |  |
| Objective | Lead | Supporting partners / stakeholders | Milestone / Measure of success |  |
| 2.1 Work with partners to deliver business crime prevention and support - Facilitate the Safe & Secure Working Group - Host bi-monthly drop-in sessions for businesses to raise and discuss safety concerns with the BBAC Coordinator, Town Centre Rangers, and Neighbourhood Police - Deliver retail crime focused advice & support including meetings, newsletters - Continue the DISC crime information sharing system - Oversee the smooth running of the smart townlink radio scheme - Deliver and support crime reduction initiatives - Promote crime reporting - Support the implementation of new Respect Orders by gathering evidence of anti-social behaviour to assist enforcement. | Blackburn BID / BBAC & Events Coordinator | BwD Council Community Safety The Mall Blackburn Lancashire Police | - Number of and attendance at working group meetings - Number of and attendance at bi-monthly drop in sessions - Increase the number of active DISC users - Number of radios actively used - Levels of crime reporting - Number of hours of Town Centre Ranger / security patrols delivered - Number of incidents dealt with by Town Centre Rangers - Positive feedback on security patrols / street rangers - Number of Respect Orders in place |  |
| 2.2 Improve perception of crime and ASB in Blackburn town centre - Deliver Town Centre Ranger service and, where possible, increase hours - Support security at events in Blackburn town centre - Regular updates for BID members - Promotion of BID and partner service delivery - Explore award opportunities for partnership projects and services - Investigate improvements to key gateways and identified areas within the BID zone to enhance public safety and perceptions of security. | BwD Council Community Safety team / Lancashire Police | Blackburn BID Chase Services / External provider BwD Council CCTV Hub Lancashire Police BwD Council Community Safety team BwD Housing Needs team The Mall Blackburn Calico Recovery Partnership | - Reduction in recorded crime - Number of hours of Town Centre Ranger / security patrols delivered - Number of incidents dealt with by Town Centre Rangers - Positive feedback on security patrols / street rangers |  |
| 2.3 Work with partners to tackle ASB / rough sleeping / begging - Multi-agency working & problem solving | BwD Council | Blackburn BID Lancashire Police Calico Recovery Service BwD Housing Needs BwD Community Safety Regional networks | - Positive feedback from stakeholders | In-kind support |

| PRIORITY THEME 3: MAKING THE TOWN CENTRE CLEANER, GREENER & MORE SUSTAINABLE |  |  |  |  |
| --- | --- | --- | --- | --- |
| Proposed Spend £5,000 |  |  |  |  |
| Objective | Lead | Supporting partners / stakeholders | Milestone / Measure of success |  |
| 3.1 Growing Places - Working in partnership with Lancashire Wildlife Trust, support charities, community groups, schools, volunteers and BID members, to carry out planting and maintenance of Growing Places projects - Collaborate with community groups to build capacity for independent maintenance of planters between scheduled gardening sessions. - Continue station adoption initiatives at Blackburn Train Station, focusing on its role as a key gateway to the town. - Seek additional funding to enhance the Growing Places project at Blackburn Train Station - Carry out targeted environmental improvements in identified areas including Victoria Gardens | Blackburn BID | Lancashire Wildlife Trust BwD Council The Mall Blackburn Purple Patch Blackburn Train Station / Northern Rail Blackburn Youth Zone Nightsafe Blackburn Schools Town centre businesses Blackburn College Age UK CANW BwD Adult Learning | - Number of partner organisations involved - Number of planting sessions - Number of volunteer hours - RHS Award |  |
| 3.2 Showcase and promote green spaces in the town centre - Promote and deliver town centre health walks - Work with an artist to design and install more interpretation signage for work at Blackburn Train Station | Blackburn BID | BwD Council The Mall Blackburn Town centre businesses | - Level of engagement with walks, in person or via social media |  |
| 3.3 Continue to support the improvement of cleanliness and planting in the town centre - Support town centre cleaning through organised litter picking - Support development / improvement of town centre green spaces | BwD Council | The Mall Blackburn BBAC Town centre businesses Blackburn BID | - Positive feedback from BID members and visitors | In-kind support |

| PRIORITY THEME 4: SUPPORTING BUSINESSES WITH INFORMATION & ADVICE |  |  |  |  |
| --- | --- | --- | --- | --- |
| Proposed Spend £3,500 |  |  |  |  |
| Objective | Lead | Supporting partners / stakeholders | Milestone / Measure of success |  |
| - Advice, support & training for Businesses - Regular BID member comms including email updates, e-newsletters, BID member website - Provide businesses with regular footfall data for the BID area to inform decision making and planning via monthly newsletters. - Signposting to business advice & support - Support the provision of free or reduced cost workshops & training sessions where there is a need - Launch a WhatsApp channel to provide timely updates and critical information. | Blackburn BID | Blackburn BID Members BwD Council Boost Lancashire | - Hours of support / advice / training provided - No. of businesses receiving 121 support - No. of BID member updates provided - No. of people signed up to WhatsApp. - Annual Review published and distributed |  |